/* ESTIMATES ARE VERY ROUGH APPROXIMATIONS */

digraph performance {

gdfo_api -> gdfo_cache;

gdfo_api -> gdfo_usage;

gdfo_api[label="GDFO API\n1 day"];

gdfo_cache[label="GDFO Cache\n1 week"];

gdfo_usage[label="GDFO Usage\n3 days"];

data_collation[label="Data co-location API\n1 month"];

repository_stacking[label="Repository stacking API\n2 months"];

bundle_container[label="Bundle container format\n2 weeks"]

xdelta[label="Xdelta sanity/learning\n2 weeks"];

xdelta_imp[label="Xdelta implementation\n1 week"];

xdelta -> xdelta_imp;

q_splitting[label="Question radix directory splitting\n2 weeks"];

i_splitting[label="Implement inventory splitting\n6-8 weeks"]

q_splitting -> i_splitting;

get_weave[label="deprecate get_weave\n1 week"];

per_file_graph -> get_weave;

per_file_graph[label="Access for per-file graph data\n1 days"];

repo_apis[label="For each use case, build targeted repo agnostic APIs\n10-40 days"];

rev_validators[label="Revision validators (use in GPG sigs etc) may poly\n3 days"];

anno_cache[label="Annotations become a cache:\n logically separate data\n2 weeks"]

anno_regen[label="Annotation regeneration\n"];

anno_kinds[label="Different styles of annotation"];

anno_regen -> anno_kinds;

anno_cache -> anno_regen;

memory_copies[label="Stop requiring full memory copies of files"];

wt_disk_order[label="Working Tree disk ordering\n6-8 weeks"];

repo_disk_order[label="Repository disk ordering\n1 month"];

graph_api[label="Network-efficient revision-graph API\n3 week"];

iter_merge[label="iter_changes based merge\n2 days"];

}